# IoT Defense V3 — Work Plan & Weekly Timeline

Structured 16-week project roadmap including environment setup, topology design, telemetry collection, AI model development, SIEM integration, and system validation.

# Executive Summary & Milestones

| Phase | Duration | Core Focus Areas | Key Deliverables |
| --- | --- | --- | --- |
| Phase 1 | Weeks 1 – 4 | Environment Setup & Initial AI Modeling | Scope definition, GNS3/VMware bridging, AI baseline code |
| Phase 2 | Weeks 5 – 8 | Topology Deployment & Telemetry | 10.10.10.0/24 LAN setup, MQTT broker, MITRE ATT&CK alignment |
| Phase 3 | Weeks 9 – 12 | AI Refinement & SIEM Integration | Threshold tuning, SIEM dashboard hook, RL framework setup |
| Phase 4 | Weeks 13 – 16 | Response Testing & System Validation | Automated mitigation, end-to-end testing, final documentation |

# Phase 1: Project Initiation, Environment Setup & Initial AI Modeling (Weeks 1 – 4)

## Week 1

- Status: ‏ Completed

- Tasks & Deliverables:

  - Collect project files, background documentation, and initial requirements.

  - Define project scope, core objectives, system architecture, and team responsibilities.

## Week 2

- Status: Completed

- Tasks & Deliverables:

  - Conduct requirements analysis and organize constraints and specifications.

  - Establish data structures, project milestones, and initial documentation baselines.

## Week 3

- Status: Completed

- Tasks & Deliverables:

  - Install and configure VMware Workstation and the GNS3 VM environment.

  - Deploy required base operating systems (Ubuntu Desktop/Gateway) and essential software dependencies.

  - Parallel Development: Initiate foundational code for the initial AI Model baseline.

## Week 4

- Status: Partial / verify

- Tasks & Deliverables:

  - Establish network adapters, interface bindings, and bridges between GNS3 and VMware.

  - Perform network troubleshooting, resolve connection errors, and ensure VM adapter compatibility.

  - Refine and validate the initial AI Model code structure.

# Phase 2: Topology Deployment, MQTT Integration & Telemetry (Weeks 5 – 8)

## Week 5

- Status: Current focus

- Tasks & Deliverables:

  - Design and construct the GNS3 network topology (10.10.10.0/24 internal LAN).

  - Configure device nodes (Linux-Gateway, Publisher-A, Publisher-B, Separate-Controller, Ethernet Switch).

  - Note: Topology is established as a dynamic architecture open to continuous refinement.

## Week 6

- Status: Planned

- Tasks & Deliverables:

  - Configure Mosquitto MQTT Broker on Linux-Gateway (10.10.10.10:1883).

  - Validate end-to-end MQTT connectivity from Publisher-A and Publisher-B to Gateway.

  - Verify IP addressing and connectivity for the Separate Controller (10.10.10.30).

## Week 7

- Status: Planned

- Tasks & Deliverables:

  - Design normal and attack telemetry generation scenarios in the lab.

  - Align logging scenarios with MITRE ATT&CK techniques (e.g., discovery and authentication attempts).

## Week 8

- Status: Planned

- Tasks & Deliverables:

  - Train and evaluate the ML/Regression baseline model using segregated normal and attack datasets.

  - Record performance metrics, dataset splits, and baseline detection limitations.

# Phase 3: AI Engine Refinement, SIEM Handoff & Policy Modeling (Weeks 9 – 12)

## Week 9

- Status: Planned

- Tasks & Deliverables:

  - Evaluate per-device regression behavior on separate baseline and test data.

  - Tune anomaly detection thresholds for network traffic patterns and payload rates.

## Week 10

- Status: Planned

- Tasks & Deliverables:

  - Connect live MQTT telemetry stream or CSV replay to the AI decision engine.

  - Define data output schema and integrate prediction results with the SIEM Dashboard.

## Week 11

- Status: Planned

- Tasks & Deliverables:

  - Implement rule fusion combining neural anomaly scores with symbolic safety rules.

  - Calibrate threat severity levels (policy_severity) and risk scoring thresholds.

## Week 12

- Status: Planned

- Tasks & Deliverables:

  - Formalize Reinforcement Learning (RL) decision framework.

  - Define state representations, action spaces, reward functions, and penalty bounds for network mitigations.

# Phase 4: Response Testing, Full Validation & Handoff (Weeks 13 – 16)

## Week 13

- Status: Planned

- Tasks & Deliverables:

  - Train and evaluate the RL mitigation policy within simulated network attack scenarios.

## Week 14

- Status: Planned

- Tasks & Deliverables:

  - Test automated response mechanisms in GNS3 (Dry-run mode, approval flows, logging, and rollback).

## Week 15

- Status: Planned

- Tasks & Deliverables:

  - Conduct full end-to-end system integration testing across GNS3 topology, AI Engine, and SIEM Dashboard.

  - Verify overall system resilience and extended operational stability.

## Week 16

- Status: Planned

- Tasks & Deliverables:

  - Complete technical documentation (Network Infrastructure 5.1 & ZEUS AI Engine 5.3).

  - Perform final code audit, consolidate diagrams and topology files, and complete project submission.